|  |  |  |  |
| --- | --- | --- | --- |
|  | Responsible Parties  | Est. Timeline | ITC Alternate Proposal  |
| PMC present proposal to independent evaluator  |  PMC | Within 30 days of posting the *draft* Regional Transmission Plan | 15 Days |
| Issue RFI | Independent Evaluator drafts RFI, PMC issues RFI | Within 30 days of posting the *final* Regional Transmission Plan | 15 days  |
| RFI Responses Due  | Eligible Developers  | 10 days following issuance of RFI  |  |
| Post list of interested developers | PMC | 7days following RFI deadline |  |
| Issue RFP | Independent evaluator drafts RFP, PMC issues RFP | Within 10 business days following posting of interested developers | Within 30 days following posting of interested developers |
| RFP Responses Due  | Interested developers  | ?? 60 days ?? | 120 days |
| Bids Reviewed for Completeness | Independent Evaluator | Within 30 days following bid deadline | Within 15 days following bid deadline |
| Opportunity to cure deficiencies  | Developers  | 14 days following notification of missing information |  |
| Bid presentations | Developers  | Within 30 days following bid deadline |  |
| Bid evaluations  | Independent Evaluator | 90 days |  |
| Review of preliminary developer selection recommendations | Beneficiaries | 30 days | 15 days following issuance of preliminary recommendations |
| Final developer selection recommendation | Independent evaluator | 30 days following beneficiary review of preliminary recommendations  | 10 days following beneficiary review of preliminary recommendations |
| Developer selected  | PMC | Next PMC meeting, at least 30 days following receipt of final recommendation  | Call special PMC meeting to expedite this step to < 1 mo. |
| Post-Selection Document | Independent Evaluator and PMC  | Within 60 days of selecting a developer  |  |
| Submit project development schedule to PMC  | Selected developer  | Within 30 days of notifying selected developer  | May be unnecessary as project schedule should be included in bid. |