## Slide 1: WestConnect Developer Selection Process Task Force
Webinar
October 26, 2016
Revised 11/3/2016

## Slide 2
Welcome
&
Introductions
Bob Smith, PMC Vice-Chair, TransCanyon

## Slide 3
Antitrust Statement Reminder
Bob Smith, PMC Vice-Chair, TransCanyon

## Slide 4: Process Steps and Timeline Review

## Slide 5: Developer Selection Process Steps - Draft
Process Step | Responsible Parties | Est. Timeline:
Create pool of independent evaluators Screen pool of evaluators and select an evaluator for each project selected into the Regional Plan for purposes of cost allocation | PMC PMC *with no special involvement from the project beneficiaries* | To be developed To be developed
Present project(s) selected into the Regional Plan for purposes of cost allocation to independent evaluator | PMC with involvement from the Beneficiaries *meeting will be public* | Within 30 days of posting the draft Regional Transmission Plan
Issue RFI RFI responses due Post list of interested developers | Independent evaluator drafts RFI PMC issues RFI Eligible developers PMC | Within 15 days of posting the final Regional Transmission Plan 30 days following issuance of RFI 7 days following RFI deadline
Continued onto next page… |  | 
Revised 10/27/16

## Slide 6: Developer Selection Process Steps, cont.- Draft
Process Step | Responsible Parties | Est. Timeline:
Issue RFP RFP responses due Bids reviewed for completeness Opportunity to cure deficiencies Bid presentations to independent evaluator *under discussion* | Independent evaluator drafts RFP PMC issues RFP Interested developers Independent evaluator Developers Developers (others to be involved? Open vs. closed meetings?) | 30 days following RFI deadline 90 days Within 30 days following bid deadline 14 days following notification of missing information Within 30 days following bid deadline
Bid evaluations | Independent evaluator | 120 days following review for completeness
Developer selection recommendation to PMC Developer selected Post document explaining why a developer was/was not selected | Independent evaluator PMC Independent evaluator and PMC | Within 14 days following the end of the bid evaluation period Next PMC meeting, no less than 30 days and more than 45 days following receipt of final recommendations Within 60 days of selecting a developer (per tariff language)
Forward project development schedule to PMC | Selected developer | Within 30 days of notifying selected developer
Revised 10/27/16

## Slide 7: Approximate Developer Selection Timeline - Draft
Chart: 
| Draft Regional Plan Posted | Final Regional Plan Posted | Issue RFI | RFI Responses Due | Issue RFP | RFP Responses Due | Bids Reviewed for Completeness | Final Developer Selection Recommendations to PMC | Developer Selected
POSITION | -5 | 5 | 10 | 8 | 10 | 8 | 6 | 8 | 6
DATE | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
PMC present projects to IE
Bid Presentations
Revised 10/27/16

## Slide 8: Developer Qualification and Selection Strawman

## Slide 9: Developer Qualification and Selection Strawman
Proposed 3-phase process
  Developer Qualification
    Existing process, no changes proposed
    Qualitative assessment to determine if a developer has generally sufficient experience and capabilities to develop, finance, build, own, operate and maintain a transmission facility
    This is not a project-specific assessment
  Developer Selection Part I (focus of strawman)
    Qualitative assessment of an Eligible Developer’s capabilities to develop, finance, build, own, operate and maintain a specific project selected into the Regional Plan for purposes of cost allocation
    If only 1 Eligible Developer responds to an RFP, the process stops here (Thoughts? What’s the point of scoring unless you have competing proposals?)
  Developer Selection Part II (focus of strawman)
    Quantitative evaluation to select among competing Eligible Developers
    Scoring matrix developed on a project-by-project basis (see additional detail on subsequent slides)

## Slide 10: Developer Qualification Evaluation Criteria
Link to existing Developer Qualification Application (https://doc.westconnect.com/Documents.aspx?NID=17184)
“The intent of WestConnect in seeking the requested information is to enable a high level screening evaluation of the Transmission Developer Applicant’s (Applicant’s) ability (and other entities that it proposes to work with and rely upon) to carry out the required tasks and responsibilities associated with developing, financing, building, owning, operating and maintaining a transmission facility that is approved for cost allocation.”
Qualification criteria:
  The Applicant has demonstrated the capability to license, design, engineer, procure material and equipment, site and route, acquire Right-of- Way (ROW), project manage, and construct large transmission projects.
  The Applicant is able to be compliant with NERC and/or Regional Entity Reliability Standards and/or other regulatory requirements pertaining to the development, construction, ownership, operation, and/or maintenance of electric transmission facilities.
  The Applicant will participate in the Regional Planning Process and other applicable planning forums for the identification, analysis, and communication of transmission projects.
  The Applicant has demonstrated creditworthiness and adequate capital resources to finance transmission projects.
  The Applicant has demonstrated that it has or has plans to develop an adequate internal safety program, contractor safety program, safety performance record and program execution.
  The Applicant will be able to operate and maintain a transmission project in accordance with Good Utility Practice and in compliance with all NERC and/or Regional Entity Reliability Standards.

## Slide 11: Proposed Evaluation Criteria for Developer Selection Part I
Design:
Does the proposed project design meet the regional transmission need consistent with the project as defined in the Regional Plan?
Does the proposed project design satisfy all applicable reliability standards and criteria (e.g. NERC, WECC, beneficiary)
Criteria considered will include:
    Detailed proposed project description and route
    Design parameters
      Design alternatives considered to facilities/equipment
    Design life of equipment and facilities

## Slide 12: Proposed Evaluation Criteria for Developer Selection Part I
Development of Project and Construction:
  Has the Eligible Developer demonstrated that it has assembled, or has plans to assemble a sufficiently-sized team with the manpower, equipment, knowledge and skill required to license, design, engineer, procure material and equipment, site and route, acquire Right-of- Way (ROW), project manage, and construct the project such that the completion of the project is consistent with the need date identified in the Regional Plan?
  Does the Eligible Developer and its team meet applicable state requirements and/or beneficiary policies related to diversity?
  Criteria considered will include:
    Detailed staff and third-party contractor strength (including relevant experience and capabilities) proposed for the development and construction of the project (proof of definitive agreements with third-party contractors is required)
    Detailed project development and construction plan (see next slide)
    Proposed schedule for development and completion of the project

## Slide 13: Proposed Evaluation Criteria for Developer Selection Part I
Development of Project and Construction, continued:
  Detailed project development and construction plan should address the following areas:
    Capital procurement for project funding
    Project management (including cost and schedule control)
    Transmission line routing studies and/or substation siting studies
    Regulatory permitting (state and federal) including preparation, filing, legal support, and testimony.
    Right-of-way and other real estate acquisition abilities, including procedures and historic practices exhibiting sound ROW and land management, particularly as it relates to siting or routing transmission facilities through environmentally sensitive areas and mitigation thereof.
    Preliminary engineering, design, and land surveying for regulatory filing and routing study support
    Detailed engineering, design, and land surveying for the final design package
    Material Bidding and Procurement
    Construction
    Commissioning and Testing
    *Schedule and budget for individual items should be a provided
    **References to pre-existing procedures and practices should be provided

## Slide 14: Proposed Evaluation Criteria for Developer Selection Part I
Operations and Maintenance:
  Has the Eligible Developer demonstrated that it is capable to undertake the operation and maintenance of the project?
  Criteria considered will include:
    Capabilities and plan for project operations
    Capabilities and plan for project maintenance (including staffing, equipment, crew training, and facilities)
    Security program and plan
    Storm/outage response plan
    Safety program

## Slide 15: Proposed Evaluation Criteria for Developer Selection Part I
Financing:
  Has the Eligible Developer demonstrated that it has sufficient financial resources to develop, build, operate and maintain the project?
  Criteria considered will include:
    financing plan (sources debt and equity), including construction financing and long-term financing
    ability to finance restoration/forced outages
    credit ratings
    financial statements

## Slide 16: Proposed Evaluation Criteria for Developer Selection Part I
Cost:
  What is the proposed cost to design, construct, operate, and maintain the project?
  Does the proposed cost of the facility produce a cost-to-benefit ratio (CBR) greater than or equal to the CBR of the project as defined in the Regional Plan?
  Criteria considered will include:
    total project cost (development, construction, financing, and other non-O&M costs)
    operation and maintenance costs, including evaluation of electrical losses (discuss the losses piece)
    revenue requirement, including proposed cost of equity, FERC incentives, proposed cost of debt and total revenue requirement calculation
    present value cost of project to beneficiaries.
    plans for cost containment

## Slide 17: Proposed Evaluation Criteria for Developer Selection Part II
Focus is on quantitative aspects of criteria addressed in Part I and project-specific experience and capabilities (i.e. demonstrated capabilities) in order to do a comparative assessment of competing bids
  There may be overlap in Part I and Part II criteria. Collectively, the criteria from Part I and Part II will establish what information will be required in the bid submittals
Possible Criteria Categories for Scoring Matrix:
  Project Plan (to include design, construction, operations, and maintenance)
  Schedule
  Cost
  Financing
  Planning Participation

## Slide 18: Proposed Evaluation Criteria for Developer Selection Part II
  Project Plan (to include design, construction, operations, and maintenance – break out separately?)
    Criteria considered will include:
      Technical and engineering qualifications and experience of the proposed staff and third-party contractor support
      Relevant experience and capabilities regarding construction, scheduling, operating, and maintenance of transmission facilities (we could break this out into expertise and track record in specific areas like environmental, ROW acquisition, procurement, construction, commissioning, safety, reliability/compliance etc.)
      Expected electrical losses (design efficiency)
      Estimated life of construction
      Description of existing right of way or substations that could be utilized for the project
      Any other strengths and advantages the Eligible Developer and its team may have to facilitate the development and construction of the project

## Slide 19: Proposed Evaluation Criteria for Developer Selection Part II
  Schedule
    Criteria considered will include:
      Proposed schedule for development and completion of the project and demonstrated ability to meet that schedule
  Cost
    Criteria considered will include:
      total project cost (development, construction, financing, and other non-O&M costs)
      operation and maintenance costs, including evaluation of electrical losses
      revenue requirement, including proposed cost of equity, FERC incentives, proposed cost of debt and total revenue requirement calculation
      present value cost of project to beneficiaries.
      plans for cost containment and demonstrated cost containment capability

## Slide 20: Proposed Evaluation Criteria for Developer Selection Part II
  Financing
    Criteria considered will include:
      Financial resources (to be further specified) of the Eligible Developer and its team
  Planning Participation
    Criteria considered will include:
      Did the Eligible Developer submit a credible project to satisfy any regional need (i.e. reliability, economic, or public policy)?

## Slide 21: Proposed Scoring Matrix Approach
Maximum points established for each major criteria category (e.g. SPP process)
Specific weights to be set by the PMC in consultation with the beneficiaries and the independent evaluator
Cost will be weighted at least 50% of the quantitative criteria (Part II criteria)
Planning Credit will be weighted 5% for all project solicitations

## Slide 22: Scoring Matrix Discussion
Criteria Category | Maximum Weighting
Project Plan Sub categories, e.g. Design, Construction, O&M? | e.g. max set to 30% of total, specific level to be set by PMC e.g. overall category weighting could be distributed among the subcategories by the PMC
Schedule | e.g. max set to 10% of total, specific level to be set by PMC
Cost | Not less than 50%
Financing | e.g. max set to 5% of total, specific level to be set by PMC
Planning Participation | 5% (does not change)
Others? | 

## Slide 23: Scoring Matrix Example
Criteria Category | Maximum Weighting
Project Plan Engineering/Design Permitting/Environmental Construction/Procurement O&M | 10% 10% 10% 5%
Schedule | 10%
Cost | 50%
Planning Participation | 5%

## Slide 24: Draft Procedures Document

## Slide 25: Action Items and Next Steps

## Slide 26
November 22nd - 2:00 p.m. to 4:00 p.m. (MST)/ 1:00 p.m. to 3:00 p.m. (PST) – webinar
  Brattle Group and ICF will join the call to provide feedback on what we’ve developed to-date
26
Next Meeting

## Slide 27: Adjourn