## Slide 1: WestConnect Developer Selection Process Task Force
Webinar
December 19, 2016

## Slide 2
Welcome
&
Introductions
Bob Smith, PMC Vice-Chair, TransCanyon

## Slide 3
Antitrust Statement Reminder
Bob Smith, PMC Vice-Chair, TransCanyon

## Slide 4: Process Steps and Timeline Review

## Slide 5: Developer Selection Process Steps - Draft
Process Step | Responsible Parties | Est. Timeline:
Create pool of independent evaluators Screen pool of evaluators and select an evaluator for each project selected into the Regional Plan for purposes of cost allocation | PMC PMC *with no special involvement from the project beneficiaries* | To be developed To be developed
Present project(s) selected into the Regional Plan for purposes of cost allocation to independent evaluator | PMC with involvement from the Beneficiaries *meeting will be public* | Within 30 days of posting the draft Regional Transmission Plan
Issue RFI RFI responses due Post list of interested developers | Independent evaluator drafts RFI PMC issues RFI Eligible developers PMC | Within 15 days of posting the final Regional Transmission Plan 30 days following issuance of RFI 7 days following RFI deadline
Continued onto next page… |  | 
Revised 10/27/16

## Slide 6: Developer Selection Process Steps, cont.- Draft
Process Step | Responsible Parties | Est. Timeline:
Issue RFP RFP responses due Bids reviewed for completeness Opportunity to cure deficiencies Bid presentations to independent evaluator *under discussion* | Independent evaluator drafts RFP PMC issues RFP Interested developers Independent evaluator Developers Developers (others to be involved? Open vs. closed meetings?) | 30 days following RFI deadline 90 days Within 30 days following bid deadline 14 days following notification of missing information Within 30 days following bid deadline
Bid evaluations | Independent evaluator | 120 days following review for completeness
Developer selection recommendation to PMC Developer selected Post document explaining why a developer was/was not selected | Independent evaluator PMC Independent evaluator and PMC | Within 14 days following the end of the bid evaluation period Next PMC meeting, no less than 30 days and more than 45 days following receipt of final recommendations Within 60 days of selecting a developer (per tariff language)
Forward project development schedule to PMC | Selected developer | Within 30 days of notifying selected developer
Revised 11/22/16
Notes: Based on feedback received from Brattle and ICF, discussion on 11/22 suggested we should not explicitly identify an opportunity for the bidders to present to the IE. This aspect is not worth the potential risk of litigation. Rather, the IE should have adequate/transparent methods in place to have their questions answered.

## Slide 7: Approximate Developer Selection Timeline - Draft
Revised 11/22/16

## Slide 8: Selecting an Independent Evaluator Strawman
Tom Wrenbeck, ITC
Devin McMackin, ITC
Heidi Pacini, WestConnect

## Slide 9: Options for an Independent Evaluator
 | Pros | Cons
“Pool of IEs” IE selected from among a pool of firms once projects are known | Multiple options to avoid COI Single entity conducting the evaluation process IE can subcontract to bring in additional expertise as-needed | If we are unable to identify a pool of firms without a real or perceived COI in a given cycle – likelihood of this happening?
“IE Manager” Hire a firm to populate and manage a panel of independent Subject Matter Experts (SMEs) | A firm with a real or perceived COI could still manage the selection process for WestConnect (if you disagree, this moves to “con” column) | Difficulty in finding qualified SMEs to populate the panel Is it possible to get sufficient breadth of experts? Bandwidth to handle multiple projects under solicitation Continuity from cycle to cycle
Notes: Independent Evaluators may have potential or perceived conflicts due to prior or current work associated with Transmission Projects or specific Developers that submit bids.

## Slide 10: Recommended Option
“Pool of IEs”
  ICF recommendation: at least 3 firms should be identified for the pool
  Service agreements should be executed with each firm well in advance of needing to initiate the selection process (see proposed schedule on slide 13)
Assumptions:
  Single IE conducts entire selection process (for all projects selected in Plan for purposes of cost allocation)
    Risks - Does the firm have enough bandwidth to meet the process deadlines if there are multiple projects selected for purposes of cost allocation? What if no single firm is free of COI on all projects? – this should be a consideration when establishing the pool
    Alternative - Select “best” IE to conduct the selection process for each applicable project – Concern: consistency in evaluation approach from project to project?
  The pool will be established once, and each subsequent cycle WestConnect will need to confirm “qualified” firms are still available and free of COI as needed/applicable
    Select new or additional IEs only as-needed

## Slide 11: Phase 1 - Establishing a Pool of Firms
Considerations:
  General Billing Rates i.e. cost
    In order to determine if rates are generally reasonable in the event only 1 IE from the pool is not conflicted out in a given cycle
  General Qualifications and Experience
    Experience evaluating bids
    Qualifications to evaluate the developer selection evaluation criteria (e.g. design, construction, O&M, financing, etc.)
    Experience with energy infrastructure development
  COI check against all Eligible Developers and any projects currently under development in the WestConnect region
    This will give us an idea as to how many IEs we need in the pool
Similar to Developer Qualification process

## Slide 12: Phase 2 - Selecting the IE to Conduct the Evaluations
Considerations:
  Specific Billing Rates given the particular scope and schedule of the evaluations
  Particular experience related to the specific project(s) selected in the Plan for purposes of cost allocation
    E.g. Experience with DC lines if the project selected is a DC line
    E.g. Experience in a given state or service territories, etc.
  COI check against specific project(s) selected in the Plan for purposes of cost allocation (For task force discussion: Do we need to wait for RFI responses before we do the final COI check and pick the final IE? Depending on the answer to this, we may need to adjust the proposed schedule and the entity responsible for drafting the RFI.)

## Slide 13: Proposed Schedule/Timing for Selecting the IEs
Initiate Phase 1 on May 1 of Year 2
  Issue RFI if a regional need has been identified and project ideas have been submitted in earlier phases of regional planning process
  Select pool of firms by July 31 (3 months to create the pool)
Select the particular IE no later than November 1 of Year 2
  Recall, developer selection process timeline requires max of 30 days following posting of draft Plan for PMC to present projects selected for purposes of cost allocation to the IE responsible for drafting the RFIs/RFPs
  RFI for developer selection must be issued no later than 15 days following posting of the final Regional Plan
Notes: In the current planning cycle (2016/17), as soon as it’s determined WestConnect will have regional needs, we should begin preparing to execute Phase 1

## Slide 14
Proposed IE selection timeline

## Slide 15: Procedure Document Update

## Slide 16: Action Items and Next Steps

## Slide 17
Tentative: January 25th - 2:00 p.m. to 4:00 p.m. (MST)/ 1:00 p.m. to 3:00 p.m. (PST) – webinar
17
Next Meeting

## Slide 18: Adjourn